## Sheet1
|  |  | Ivan Zakhartchuok | Michael Koltashew
| Task | Details | Est1 | Est2 | AssignedTo | Est | Spent
1 | setup environment | create project, add to Git, | 3 | 2 | Michael | 2 | 1
2 | create DB structure | necessary tables and relations | 2 | 4 | Ivan | 2 | 2
3 | implement DAL | DbContext, migrations, repositories, UoW; DAL models | 5 | 6 | Michael | 6 | 7
| services layer | services, mapper config, DI config | 6 | 5 | Michael | 5 | 6
4 | implement basic BLL functional | BLL models | 2 | 3 | Ivan | 2 | 2
5 | authentication/registration |  | 5 | 3 | Michael | 3 | 3
6 | user, role, cinema management | CRUD | 15 | 12 | Michael | 12
7 | user list management | CRUD | 7 | 5 | Michael | 5 | 5
8 | film management | CRUD + seance partial | 16 | 10 | Ivan | 16
9 | main page | film list | 14 | 12
10 | film page | film details | 19 | 20
11 | payment page [select seat] | select seat | 12 | 11
12 | payment page [payment method] | select payment method | 10 | 13
13 | user info page | user info management and viewing tickets | 8 | 7